## CONSOLIDATED DASHBOARD
CONSOLIDATED PORTFOLIO DASHBOARD — IME Division ¦ June 2026 ¦ AI-Generated Draft
Auto-consolidated from Sources 1–4. Human review required before distribution to Division Leadership.
Project ID | Project Name | Funder | Budget (€) | Spend YTD (€) | Budget % | HR Utilisation % | Milestone Status | Overall Status | Escalation? | Next Milestone | Key Risk / Action Required
IME-001 | Industrial Energy Efficiency Programme | BMWK | 320000 | 285000 | 89% | 66% | 1 overdue | Red | Yes | Extension approval | URGENT: No-cost extension needed by June 30. Budget critical.
IME-002 | Hydrogen Readiness SME Network | EU Horizon | 540000 | 198000 | 37% | 79% | On track | Green | No | Workshop #2 Jul 15 | On track. Partner engagement exceeds targets.
IME-003 | Mobility Transition NRW — Phase II | BMWK | 210000 | 204000 | 97% | 61% | 1 overdue | Amber | No | Interim report Jul 1 | Funder meeting overdue 31 days. Budget overrun ~€6k projected.
IME-004 | Building Renovation Accelerator | KfW | 480000 | 89000 | 19% | 82% | On track | Green | No | Site selection Aug 31 | On track. 3/5 pilot sites confirmed.
IME-005 | Industrial Heat Pump Market Study | BMWK | 95000 | 91000 | 96% | 74% | Delayed | Amber | No | Publication Aug 15 | Minor overrun. Publication delayed 3 weeks.
IME-006 | EV Fleet Transition — Public Sector | BMDV | 275000 | 132000 | 48% | 75% | On track | Green | No | Review Jul 30 | On track. Strong municipal engagement.
IME-007 | Energy Audit Digital Platform | EU LIFE | 185000 | 192000 | 104% | 91% | Critical | Red | Yes | Revised go-live Jul 31 | URGENT: IT integration failure. Vendor unresponsive. Management escalation needed.
IME-008 | Carbon Neutrality Roadmap | BMWK | 390000 | 54000 | 14% | 74% | On track | Green | No | Board setup Jul 15 | On track. Advisory board 6/8 confirmed.
IME-009 | District Heating Transition | BMUV | 620000 | 178000 | 29% | 66% | On track | Green | No | MOU signing Aug 1 | On track. Legal review causing minor delay.
IME-010 | Smart Industry Energy Monitoring | EU Interreg | 310000 | 98000 | 32% | 88% | At risk | Amber | No | Framework Jul 31 | Partner agreements delayed. Risk to July milestone.
IME-011 | Energy Efficiency Audit SME | BMWK | 145000 | 138000 | 95% | 76% | On track | Red | Yes | Q3 cycle Jul 15 | URGENT: Only €7k remaining. 3 audits outstanding. Emergency budget review needed.
IME-012 | Green Hydrogen Production Study | BMUV | 260000 | 72000 | 28% | 65% | On track | Green | No | Interviews Jul 1 | On track. Early stage.
IME-013 | Sector Coupling Innovation Network | EU Horizon | 410000 | 155000 | 38% | 81% | On track | Green | No | Conference Sep 15 | On track. Venue TBC.
IME-014 | Low-Carbon Transport Feasibility | BMWK | 78000 | 77000 | 99% | 55% | On track | Amber | No | Final report Jul 31 | Budget nearly exhausted. Last deliverable only remaining.
IME-015 | Smart Grid Pilot — Rural Areas | KfW | 330000 | 118000 | 36% | 60% | Completed | Green | No | Field measure Aug | Milestone completed ahead of schedule.
IME-016 | Industrial Decarbonisation Roadmap | BMDV | 195000 | 44000 | 23% | 94% | Completed | Green | No | TBD | Inception report approved. Project on track.
IME-017 | Renewable Energy Communities Study | BMWK | 550000 | 223000 | 41% | 59% | On track | Amber | No | Case study Sep 1 | Two deliverables converging in September. Deadline risk.
IME-018 | Building Decarbonisation Policy Brief | EU LIFE | 125000 | 121000 | 97% | 57% | On track | Red | Yes | Policy brief Jul 15 | Budget overrun incurred. Sign-off needed for final editing costs.
IME-019 | Circular Economy Energy Materials | BMUV | 440000 | 189000 | 43% | 76% | On track | Green | No | Pilot report Aug 30 | Strong industry engagement. On track.
IME-020 | Cross-Border Energy Transition Forum | EU Interreg | 285000 | 68000 | 24% | 89% | Completed | Green | No | Forum Nov | MOU completed early. On track.
IME-021 | Energy Storage Market Analysis | BMWK | 175000 | 168000 | 96% | 85% | Overdue | Red | Yes | Revised submission | URGENT: Scope expanded without budget. Risk of overrun AND late delivery.
IME-022 | Offshore Wind Value Chain Study | KfW | 490000 | 201000 | 41% | 79% | On track | Green | No | Survey close Jul 31 | Survey response below target. Follow-up campaign active.
IME-023 | Climate-Neutral Industrial Parks | EU Horizon | 360000 | 92000 | 26% | 94% | On track | Green | No | Interim report Aug 15 | 4/8 site visits complete. On track.
IME-024 | Urban Mobility Transition Plan | BMDV | 215000 | 209000 | 97% | 89% | On track | Amber | No | Final deliverables Aug | Budget tight (€6k). Manageable if no scope changes.
IME-025 | Biomass Energy Potential Study | BMWK | 520000 | 145000 | 28% | 70% | On track | Green | No | Analysis Aug 1 | Data collection complete. Analysis phase starting.
PORTFOLIO TOTALS | [5 empty] | 0.73
PORTFOLIO HEALTH SUMMARY
Total Projects |  | 25
🟢 Green
🟡 Amber
🔴 Red
Escalations Required
Overdue Milestones |  | 5

## SOURCE 1 — SAP Finance
SOURCE 1: SAP Finance Export — Budget & Cost Data (Auto-Export, 1st of Month)
DO NOT EDIT — Raw system export. Division Controlling reads this sheet automatically.
Project ID | Cost Centre | Funder | Contract Value (€) | Approved Budget (€) | Commitments (€) | Actual Spend YTD (€) | Forecast Full Year (€) | Budget Remaining (€) | Fiscal Year
IME-001 | 194452 | BMWK | 320000 | 320000 | 12000 | 285000 | 318000 | 35000 | 2026
IME-002 | 271449 | EU Horizon | 540000 | 540000 | 45000 | 198000 | 410000 | 342000 | 2026
IME-003 | 171327 | BMWK | 210000 | 210000 | 8000 | 204000 | 215000 | 6000 | 2026
IME-004 | 192314 | KfW | 480000 | 480000 | 32000 | 89000 | 220000 | 391000 | 2026
IME-005 | 53233 | BMWK | 95000 | 95000 | 3000 | 91000 | 96000 | 4000 | 2026
IME-006 | 171946 | BMDV | 275000 | 275000 | 18000 | 132000 | 260000 | 143000 | 2026
IME-007 | 131403 | EU LIFE | 185000 | 185000 | 5000 | 192000 | 196000 | -7000 | 2026
IME-008 | 85423 | BMWK | 390000 | 390000 | 28000 | 54000 | 180000 | 336000 | 2026
IME-009 | 339922 | BMUV | 620000 | 620000 | 55000 | 178000 | 390000 | 442000 | 2026
IME-010 | 305266 | EU Interreg | 310000 | 310000 | 22000 | 98000 | 210000 | 212000 | 2026
IME-011 | 138211 | BMWK | 145000 | 145000 | 6000 | 138000 | 147000 | 7000 | 2026
IME-012 | 144667 | BMUV | 260000 | 260000 | 19000 | 72000 | 180000 | 188000 | 2026
IME-013 | 272404 | EU Horizon | 410000 | 410000 | 31000 | 155000 | 310000 | 255000 | 2026
IME-014 | 152531 | BMWK | 78000 | 78000 | 2000 | 77000 | 80000 | 1000 | 2026
IME-015 | 403025 | KfW | 330000 | 330000 | 24000 | 118000 | 270000 | 212000 | 2026
IME-016 | 159923 | BMDV | 195000 | 195000 | 14000 | 44000 | 130000 | 151000 | 2026
IME-017 | 192273 | BMWK | 550000 | 550000 | 41000 | 223000 | 480000 | 327000 | 2026
IME-018 | 252725 | EU LIFE | 125000 | 125000 | 4000 | 121000 | 127000 | 4000 | 2026
IME-019 | 50414 | BMUV | 440000 | 440000 | 33000 | 189000 | 360000 | 251000 | 2026
IME-020 | 422117 | EU Interreg | 285000 | 285000 | 20000 | 68000 | 190000 | 217000 | 2026
IME-021 | 173559 | BMWK | 175000 | 175000 | 9000 | 168000 | 178000 | 7000 | 2026
IME-022 | 172692 | KfW | 490000 | 490000 | 38000 | 201000 | 420000 | 289000 | 2026
IME-023 | 109566 | EU Horizon | 360000 | 360000 | 27000 | 92000 | 240000 | 268000 | 2026
IME-024 | 257768 | BMDV | 215000 | 215000 | 15000 | 209000 | 218000 | 6000 | 2026
IME-025 | 268587 | BMWK | 520000 | 520000 | 42000 | 145000 | 380000 | 375000 | 2026
372507

## SOURCE 2 — PL Status Input
SOURCE 2: Project Lead Monthly Status Input — June 2026
Yellow cells to be completed by Project Leads by 1st of each month. Do NOT modify grey columns.
Project ID | Project Name | Project Lead | Overall Status (Green/Amber/Red) | Key Achievement This Month | Main Risk / Issue | Escalation Needed? (Yes/No) | Free Text Update
IME-001 | Industrial Energy Efficiency Programme | Dr. A. Müller | Red | Final report 80% complete | Budget nearly exhausted, extension request pending | Yes | Urgent: need approval for 2-month no-cost extension from BMWK before June 30.
IME-002 | Hydrogen Readiness SME Network | Ms. B. Weber | Green | 30 new SME partners onboarded | None significant | No | Workshop #2 preparation on track. Partner engagement exceeds KPI targets.
IME-003 | Mobility Transition NRW — Phase II | Mr. C. Schmidt | Amber | Interim evaluation submitted | Budget overrun likely by Q3 | No | Cost overrun of ~€6k projected. Requesting reallocation from travel budget.
IME-004 | Building Renovation Accelerator | Ms. D. Fischer | Green | Pilot site selection shortlist ready | Stakeholder alignment slower than planned | No | 3 pilot sites confirmed. 2 more in negotiation. On track for August milestone.
IME-005 | Industrial Heat Pump Market Study | Dr. E. Klein | Amber | Draft publication reviewed | Minor budget overrun (€1k) | No | Final publication delayed by 3 weeks due to external review feedback.
IME-006 | EV Fleet Transition — Public Sector | Mr. F. Bauer | Green | Mid-term review meeting scheduled | None | No | Strong municipal partner engagement. Mid-term stakeholder review confirmed July 30.
IME-007 | Energy Audit Digital Platform | Ms. G. Hoffmann | Red | Platform 90% complete | Go-live delayed — IT integration issues | Yes | Critical: API integration with third-party system failing. IT vendor unresponsive. Need escalation to management.
IME-008 | Carbon Neutrality Roadmap — Chemical Sector | Dr. H. Braun | Green | Advisory board members confirmed | None | No | 6 of 8 board members confirmed. Kick-off meeting planned for July 15.
IME-009 | District Heating Transition — East Germany | Mr. I. Richter | Green | 3 municipal MOUs signed | Legal review slower than expected | No | Strong progress on partner agreements. Legal team backlog causing 2-week delay.
IME-010 | Smart Industry Energy Monitoring Pilot | Ms. J. Lange | Amber | Data framework draft complete | Partner data sharing agreements delayed | No | 2 of 5 partner agreements signed. Remaining 3 in legal review. Risk to July milestone.
IME-011 | Energy Efficiency Audit SME Programme | Mr. K. Wolf | Red | Q2 audit report submitted | Budget critically low — project at risk | Yes | Only €7k remaining. 3 planned audits still outstanding. Need emergency budget review.
IME-012 | Green Hydrogen Production Study | Ms. L. Braun | Green | Literature review complete | None | No | On track. First expert interviews scheduled for July.
IME-013 | Sector Coupling Innovation Network | Dr. M. Koch | Green | Annual conference planned | Venue confirmation pending | No | Programme committee established. Speaker confirmations ongoing.
IME-014 | Low-Carbon Transport Feasibility | Mr. N. Becker | Amber | Stakeholder mapping complete | Budget nearly consumed | No | Only €1k remaining. Final report is the last deliverable — should be sufficient.
IME-015 | Smart Grid Pilot — Rural Areas | Ms. O. Schäfer | Green | Technical partner MOU signed | None | No | Grid operator partnership confirmed. Field measurements starting August.
IME-016 | Industrial Decarbonisation Roadmap | Mr. P. Wagner | Green | Inception report approved | None | No | Project formally started. Team fully onboarded.
IME-017 | Renewable Energy Communities Study | Dr. Q. Zimmermann | Amber | Case study selection complete | Funder reporting deadline conflict | No | Two deliverables due same week in September. Requesting deadline adjustment from BMWK.
IME-018 | Building Decarbonisation Policy Brief | Ms. R. Neumann | Red | Policy brief 95% complete | Budget exhausted | Yes | €4k overrun already incurred. Final editing and translation costs exceed budget. Need sign-off.
IME-019 | Circular Economy Energy Materials | Mr. S. Schwarz | Green | Supply chain mapping complete | None | No | Strong industry engagement. 12 companies participating in pilot phase.
IME-020 | Cross-Border Energy Transition Forum | Ms. T. Schulz | Green | Partner country confirmed | None | No | Poland and Czech Republic confirmed as partner countries. Forum date set for November.
IME-021 | Energy Storage Market Analysis | Dr. U. Krause | Red | Draft analysis 70% complete | Budget overrun and deadline risk | Yes | Scope expanded by funder without budget increase. Risk of both overrun and late delivery.
IME-022 | Offshore Wind Value Chain Study | Ms. V. Hartmann | Green | Industry survey launched | Survey response rate lower than expected | No | 42% response rate so far. Follow-up campaign planned. Target is 60% by July 31.
IME-023 | Climate-Neutral Industrial Parks | Mr. W. Lorenz | Green | Site visit programme started | None | No | 4 of 8 site visits completed. Findings being documented for interim report.
IME-024 | Urban Mobility Transition Plan | Ms. X. Lehmann | Amber | City partner survey complete | Budget nearly exhausted | No | €6k remaining for final two deliverables. Tight but manageable if no scope changes.
IME-025 | Biomass Energy Potential Study | Dr. Y. Maier | Green | Regional data collection complete | None | No | Data from all 16 federal states collected. Analysis phase starting July.

## SOURCE 3 — HR Timesheet
SOURCE 3: HR Timesheet Export — Person-Days by Project (May 2026)
Auto-export from HR system. Shows planned vs. actual person-days per project lead.
Project ID | Project Name | Project Lead | Planned PD (Full Project) | Actual PD (To Date) | Remaining PD (Planned) | Utilisation %
IME-001 | Industrial Energy Efficiency Programme | Dr. A. Müller | 640 | 420 | 8
IME-002 | Hydrogen Readiness SME Network | Ms. B. Weber | 1120 | 884 | 202
IME-003 | Mobility Transition NRW — Phase II | Mr. C. Schmidt | 1600 | 983 | 4
IME-004 | Building Renovation Accelerator | Ms. D. Fischer | 1600 | 1310 | 228
IME-005 | Industrial Heat Pump Market Study | Dr. E. Klein | 1280 | 941 | 3
IME-006 | EV Fleet Transition — Public Sector | Mr. F. Bauer | 1920 | 1440 | 82
IME-007 | Energy Audit Digital Platform | Ms. G. Hoffmann | 1440 | 1317 | 2
IME-008 | Carbon Neutrality Roadmap | Dr. H. Braun | 1760 | 1310 | 198
IME-009 | District Heating Transition | Mr. I. Richter | 1120 | 741 | 256
IME-010 | Smart Industry Energy Monitoring | Ms. J. Lange | 480 | 421 | 127
IME-011 | Energy Efficiency Audit SME | Mr. K. Wolf | 1600 | 1213 | 3
IME-012 | Green Hydrogen Production Study | Ms. L. Braun | 1120 | 725 | 108
IME-013 | Sector Coupling Innovation Network | Dr. M. Koch | 1920 | 1555 | 149
IME-014 | Low-Carbon Transport Feasibility | Mr. N. Becker | 960 | 531 | 2
IME-015 | Smart Grid Pilot — Rural Areas | Ms. O. Schäfer | 1280 | 771 | 125
IME-016 | Industrial Decarbonisation Roadmap | Mr. P. Wagner | 960 | 898 | 294
IME-017 | Renewable Energy Communities Study | Dr. Q. Zimmermann | 800 | 474 | 178
IME-018 | Building Decarbonisation Policy Brief | Ms. R. Neumann | 800 | 455 | 2
IME-019 | Circular Economy Energy Materials | Mr. S. Schwarz | 480 | 365 | 148
IME-020 | Cross-Border Energy Transition Forum | Ms. T. Schulz | 1760 | 1566 | 130
IME-021 | Energy Storage Market Analysis | Dr. U. Krause | 1120 | 948 | 100
IME-022 | Offshore Wind Value Chain Study | Ms. V. Hartmann | 1280 | 1015 | 167
IME-023 | Climate-Neutral Industrial Parks | Mr. W. Lorenz | 1280 | 1205 | 119
IME-024 | Urban Mobility Transition Plan | Ms. X. Lehmann | 1920 | 1707 | 5
IME-025 | Biomass Energy Potential Study | Dr. Y. Maier | 1760 | 1226 | 152
|  |  | 960 | 703

## SOURCE 4 — Milestone Tracker
SOURCE 4: Milestone Tracker — Planned vs. Actual (Updated by Project Leads)
All milestones for current reporting period. Overdue = planned date passed without completion.
Project ID | Project Name | Milestone Description | Planned Date | Actual Date (if reached) | Status | Days Overdue (if applicable) | Notes
IME-001 | Industrial Energy Efficiency | Final report submission | 2026-06-30 |  | Overdue |  | Extension request submitted to BMWK
IME-001 | Industrial Energy Efficiency | Project closure meeting | 2026-07-15 |  | Upcoming |  | Dependent on extension approval
IME-002 | Hydrogen SME Network | Stakeholder workshop #2 | 2026-07-15 |  | Upcoming |  | Venue confirmed, 45 registrations
IME-002 | Hydrogen SME Network | Partner network report Q2 | 2026-06-30 | 2026-06-28 | Completed |  | Submitted 2 days early
IME-003 | Mobility NRW Phase II | Interim evaluation report | 2026-07-01 |  | Upcoming |  | Draft 80% complete
IME-003 | Mobility NRW Phase II | Funder review meeting | 2026-05-15 |  | Overdue | 31 | Meeting postponed by funder to July
IME-004 | Building Renovation | Pilot site selection complete | 2026-08-31 |  | Upcoming |  | 3 of 5 sites confirmed
IME-005 | Heat Pump Market Study | Final publication | 2026-08-15 |  | Upcoming |  | Delayed 3 weeks from original plan
IME-006 | EV Fleet Transition | Mid-term stakeholder review | 2026-07-30 |  | Upcoming |  | Agenda drafted
IME-007 | Energy Audit Platform | Platform go-live | 2026-06-01 |  | Overdue | 14 | IT integration failure — escalated
IME-007 | Energy Audit Platform | Revised go-live target | 2026-07-31 |  | Upcoming |  | Contingent on IT resolution
IME-008 | Carbon Neutrality Roadmap | Advisory board setup | 2026-07-15 |  | Upcoming |  | 6/8 members confirmed
IME-009 | District Heating | Municipal partner agreements | 2026-08-01 |  | Upcoming |  | 3 MOUs signed, 2 pending legal
IME-010 | Smart Industry Monitoring | Data collection framework sign-off | 2026-07-31 |  | Upcoming |  | 2/5 partner agreements complete
IME-011 | SME Audit Programme | Q2 audit report | 2026-06-30 | 2026-06-29 | Completed |  | Submitted on time
IME-011 | SME Audit Programme | Q3 audit cycle start | 2026-07-15 |  | Upcoming |  | At risk — budget critically low
IME-012 | Green Hydrogen Study | Expert interview series start | 2026-07-01 |  | Upcoming |  | 8 interviews scheduled
IME-013 | Sector Coupling Network | Annual conference | 2026-09-15 |  | Upcoming |  | Venue TBC
IME-014 | Low-Carbon Transport | Final feasibility report | 2026-07-31 |  | Upcoming |  | Last deliverable — nearly complete
IME-015 | Smart Grid Pilot | Technical partner MOU | 2026-06-30 | 2026-06-25 | Completed |  | Signed ahead of schedule
IME-016 | Industrial Decarbonisation | Inception report approval | 2026-06-30 | 2026-06-30 | Completed |  | Approved on deadline
IME-017 | Renewable Energy Communities | Case study report | 2026-09-01 |  | Upcoming |  | Two deliverables converging — risk
IME-018 | Building Policy Brief | Final policy brief | 2026-07-15 |  | Upcoming |  | 95% complete — budget overrun
IME-019 | Circular Economy Materials | Pilot phase report | 2026-08-30 |  | Upcoming |  | 12 companies in pilot
IME-020 | Cross-Border Forum | Partner country MOU | 2026-06-30 | 2026-06-20 | Completed |  | Completed early
IME-021 | Energy Storage Analysis | Draft analysis submission | 2026-07-01 |  | Overdue | 14 | Scope expansion causing delay
IME-022 | Offshore Wind Study | Industry survey close | 2026-07-31 |  | Upcoming |  | 42% response rate — follow-up sent
IME-023 | Climate-Neutral Parks | Interim site visit report | 2026-08-15 |  | Upcoming |  | 4/8 visits complete
IME-024 | Urban Mobility Plan | Final deliverables | 2026-08-31 |  | Upcoming |  | Tight budget — €6k remaining
IME-025 | Biomass Potential Study | Regional analysis complete | 2026-08-01 |  | Upcoming |  | Data collection done

## AI Prompt Template
AI REPORT GENERATION — SYSTEM PROMPT TEMPLATE
Copy this prompt into n8n → Claude/GPT node. Replace <<DATA>> with CONSOLIDATED DASHBOARD content.
ROLE: | You are a senior project controlling analyst for dena (Deutsche Energie-Agentur), a German federal energy agency managing 25+ publicly funded projects.
TASK: | Analyse the consolidated project portfolio data below and generate a structured division status report for the IME Division Leadership.
REPORT STRUCTURE:
1. Executive Summary | 3–5 sentences. Overall portfolio health, total budget consumed, number of red/amber/green projects, key message for leadership.
2. Immediate Actions Required | List ONLY escalation-flagged projects. For each: project name, issue in 1 sentence, recommended action with owner and deadline.
3. Projects at Risk (Amber) | Brief note per project. What is the risk, what needs monitoring, any upcoming decision points.
4. On-Track Projects (Green) | Confirm status. Flag any milestones due in next 30 days.
5. Budget Overview | Total portfolio spend vs. budget. Any projects >90% consumed with significant time remaining. Any forecast overruns.
6. HR & Capacity | Any projects where person-day utilisation is misaligned with project stage (high utilisation + early stage, or low utilisation + late stage).
7. Recommended Leadership Actions | Max 3 bullet points. Concrete, actionable, with suggested owner.
TONE: | Professional, concise, decision-oriented. Written for a non-technical division head. No jargon.
LENGTH: | Max 700 words. Use clear section headers. Plain text only — no markdown, no bullet symbols beyond dashes.
LANGUAGE: | English.
DATA INPUT: | <<PASTE CONSOLIDATED DASHBOARD DATA HERE — copy visible cells from CONSOLIDATED DASHBOARD sheet>>